## Sheet1
Module | Task | Sub Task | Comments | Estimated Efforts in PD's
Site setup
Site provisioning
|  | Creating site columns |  | 0.5
|  | Creating content types |  | 0.5
|  | Creating lists |  | 0.5
|  | Creating list views. |  | 0.5
|  | PowerShell to Update home page with web parts |  | 1
|  | Creating group for Users, SCA's, Approvers, Responsible Persons |  | 0.5
Dashboard
User/ Admin views
|  | Get Current user type based on group he belongs |  | 0.5
|  | Update form title based on user type |  | 0.5
|  | Add and configure 4 list view web parts for admin and user |  | 1
|  | Create custom filters for filtering data. |  | 1
|  | NCA/ SHEQ view selectors |  | 0.5
|  | Add NCA and SHEQ Complaint creation buttons. |  | 0.5
|  | Create custom search box to search complaints |  | 1
NCA/ SHEQ form
Update New, View, Edit form for the list.
|  | PowerShell to update the OOB list forms |  | 1
Creating custom NCA/ SHEQ form
|  | Change form view based on user permission |  | 1
|  | Change form view based on status |  | 1
|  | Update Plant info based on plant number |  | 1
|  | Update Contact info based on Customer number |  | 1
|  | Updated product description based on pack code |  | 1
|  | Updating responsible persons in dropdown |  | 1
|  | Cascading drop down for level selection |  | 1
|  | Other form fields and logic to creation and update SharePoint list |  | 2
|  | Display form based on item selected |  | 1
Approval for NCA
Send Emails based on complaint status
|  | Send email to SCA for review |  | 1
|  | Send email to responsible person for approval |  | 1
|  | Send email to SCA and Complaint owner for resolved status |  | 1
Send Emails based on complaint status
|  | Send email to SCA for review |  | 0.5
|  | Send email to responsible person for approval |  | 0.5
|  | Send email to SCA, SHEQ Approver, Complaint owner with complaint status |  | 0.5
|  | Send email to SHEQ Approver |  | 0.5
|  | Complaint Rejected by SHEQ APPROVER Email |  | 0.5